## Sheet1
work completion scheduled days
Work completion stages |  |  |  | I | II | III | IV | V | VI | VII
Work completion percentage |  |  |  | 10% | 10% | 20% | 20% | 20% | 10% | 10%
Categories
Admin/OEM/SIC |  | A | Finalization of OEM | 10
Admin/OEM/SIC |  | B | Joint site visit by OEM team & final layouts submission
Admin/OEM/SIC |  | C | Production & delivery of lifts by OEM
| C | D | Shaft preparation Civil works before Lift Installation, scaffolding installation
| E | E | Shaft preparation Electrical works
| M | F | Old Lift Dismantling
| M | G | Mechanical Installation by OEM
| C | H | Shaft Civil works after Lift Installation
| M | E | Lift Car Installation by OEM
C | C/E | F | Finishing works
| Mechanical | G | Testing and commissioning
Admin/OEM/SIC |  | H | License
Admin/OEM/SIC |  | E | Client handover