## Sheet1
ID | Name | Start | Predecessors | Summary | Outline_Number | Outline_Level | Percent_Complete | Text1_Unitname | Number1 | Actual_Start | Actual_Finish | Duration | Constraint_Type | Constraint_Date | Task_Mode | Actual_Duration
1 | Building A |  |  | 1 | 1 | 0 | 0.000000 |  | 885419 |  |  | 0 |  |  | As Soon As Possible | 0
2 | Rcc |  |  | 1 | 2 | 1 | 0.000000 |  | 885422 |  |  | 0 |  |  | As Soon As Possible | 0
3 | Below Ground |  |  | 1 | 3 | 2 | 0.000000 |  | 885426 |  |  | 0 |  |  | As Soon As Possible | 0
4 | Below Ground RCC Coloumn M20 Cum | 24-12-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885464 | 24-12-2025 |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | -46013
5 | Below Ground RCC pardi M20 Cum | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885467 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
6 | 1ST Slab |  |  | 1 | 3 | 2 | 0.000000 |  | 885444 |  |  | 0 |  |  | As Soon As Possible | 0
7 | 1ST Slab RCC Coloumn M20 Cum | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885472 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
8 | 1ST Slab RCC pardi M20 Cum | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885475 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
9 | 1ST Slab RCC slab & beam M20 Cum | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885477 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
10 | 2ND Slab |  |  | 1 | 3 | 2 | 0.000000 |  | 885447 |  |  | 0 |  |  | As Soon As Possible | 0
11 | 2ND Slab RCC Coloumn M20 Cum | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885480 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
12 | 2ND Slab RCC pardi M20 Cum | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885481 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
13 | 2ND Slab RCC slab & beam M20 Cum | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885484 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
14 | 3RD Slab |  |  | 1 | 3 | 2 | 0.000000 |  | 885450 |  |  | 0 |  |  | As Soon As Possible | 0
15 | 3RD Slab RCC Coloumn M20 Cum | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885485 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
16 | 3RD Slab RCC pardi M20 Cum | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885486 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
17 | 3RD Slab RCC slab & beam M20 Cum | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885490 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
18 | Grooved Pointing |  |  | 1 | 2 | 1 | 0.000000 |  | 886489 |  |  | 0 |  |  | As Soon As Possible | 0
19 | Grooved Pointing Flat 101 | 09-10-2025 |  | 0 | 3 | 2 | 0.000000 |  | 886492 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
20 | Grooved Pointing Flat 102 | 09-10-2025 |  | 0 | 3 | 2 | 0.000000 |  | 886494 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
21 | Grooved Pointing Flat 103 | 09-10-2025 |  | 0 | 3 | 2 | 0.000000 |  | 886495 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
22 | Excavation For foundation |  |  | 1 | 2 | 1 | 0.000000 |  | 886604 |  |  | 0 |  |  | As Soon As Possible | 0
23 | Excavation For foundation Back filling | 09-10-2025 |  | 0 | 3 | 2 | 0.000000 |  | 886608 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
24 | Excavation For foundation Getting out | 09-10-2025 |  | 0 | 3 | 2 | 0.000000 |  | 886611 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
25 | Excavation For foundation Lead | 09-10-2025 |  | 0 | 3 | 2 | 0.000000 |  | 886612 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
26 | internal plastewring without neeru finish |  |  | 1 | 2 | 1 | 0.000000 |  | 886681 |  |  | 0 |  |  | As Soon As Possible | 0
27 | internal plastewring without neeru finish internal plasterin | 09-10-2025 |  | 0 | 3 | 2 | 0.000000 |  | 887127 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
28 | Brickwork |  |  | 1 | 2 | 1 | 0.000000 |  | 887061 |  |  | 0 |  |  | As Soon As Possible | 0
29 | tiles |  |  | 1 | 2 | 1 | 0.000000 |  | 887210 |  |  | 0 |  |  | As Soon As Possible | 0
30 | tiles tiles | 09-10-2025 |  | 0 | 3 | 2 | 0.000000 |  | 887213 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0