## Sheet1
ID | Name | Start | Predecessors | Summary | Outline_Number | Outline_Level | Percent_Complete | Text1_Unitname | Number1 | Actual_Start | Actual_Finish | Duration | Constraint_Type | Constraint_Date | Task_Mode | Actual_Duration
1 | BUILDING A |  |  | 1 | 1 | 0 | 0.000000 |  | 885179 |  |  | 0 |  |  | As Soon As Possible | 0
2 | RCC |  |  | 1 | 2 | 1 | 0.000000 |  | 885191 |  |  | 0 |  |  | As Soon As Possible | 0
3 | BELOW GROUND |  |  | 1 | 3 | 2 | 0.000000 |  | 885214 |  |  | 0 |  |  | As Soon As Possible | 0
4 | BELOW GROUND RCC COLUMN M20-Cum | 24-12-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885256 | 24-12-2025 |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | -46013
5 | BELOW GROUND Rcc pardi m20 | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885326 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
6 | 1ST SLAB |  |  | 1 | 3 | 2 | 0.000000 |  | 885496 |  |  | 0 |  |  | As Soon As Possible | 0
7 | 1ST SLAB RCC COLUMN M20-Cum | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885512 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
8 | 1ST SLAB Rcc pardi m20 | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885513 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
9 | 1ST SLAB SLABS AND BEAM | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 887425 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
10 | 2ND SLAB |  |  | 1 | 3 | 2 | 0.000000 |  | 885497 |  |  | 0 |  |  | As Soon As Possible | 0
11 | 2ND SLAB RCC COLUMN M20-Cum | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885518 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
12 | 2ND SLAB Rcc pardi m20 | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885520 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
13 | 2ND SLAB SLABS AND BEAM | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885522 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
14 | 3RD SLAB |  |  | 1 | 3 | 2 | 0.000000 |  | 885498 |  |  | 0 |  |  | As Soon As Possible | 0
15 | 3RD SLAB RCC COLUMN M20-Cum | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885524 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
16 | 3RD SLAB Rcc pardi m20 | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885526 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
17 | 3RD SLAB SLABS AND BEAM | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 885527 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
18 | Brickworks |  |  | 1 | 2 | 1 | 0.000000 |  | 887110 |  |  | 0 |  |  | As Soon As Possible | 0
19 | Excavation |  |  | 1 | 2 | 1 | 0.000000 |  | 887113 |  |  | 0 |  |  | As Soon As Possible | 0
20 | Excavation Excavation | 09-10-2025 |  | 0 | 3 | 2 | 0.000000 |  | 887268 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
21 | FGP |  |  | 1 | 2 | 1 | 0.000000 |  | 887117 |  |  | 0 |  |  | As Soon As Possible | 0
22 | Flat 101 |  |  | 1 | 3 | 2 | 0.000000 |  | 887279 |  |  | 0 |  |  | As Soon As Possible | 0
23 | Flat 101 Flush grooved pointing | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 887282 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
24 | Flat 102 |  |  | 1 | 3 | 2 | 0.000000 |  | 887280 |  |  | 0 |  |  | As Soon As Possible | 0
25 | Flat 102 Flush grooved pointing | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 887283 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
26 | Flat 103 |  |  | 1 | 3 | 2 | 0.000000 |  | 887281 |  |  | 0 |  |  | As Soon As Possible | 0
27 | Flat 103 Flush grooved pointing | 09-10-2025 |  | 0 | 4 | 3 | 0.000000 |  | 887284 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
28 | Internal plastering |  |  | 1 | 2 | 1 | 0.000000 |  | 887119 |  |  | 0 |  |  | As Soon As Possible | 0
29 | Internal plastering Flush grooved pointing | 09-10-2025 |  | 0 | 3 | 2 | 0.000000 |  | 887285 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0
30 | Vitrified tiles |  |  | 1 | 2 | 1 | 0.000000 |  | 887278 |  |  | 0 |  |  | As Soon As Possible | 0
31 | Vitrified tiles Virtified tiles | 09-10-2025 |  | 0 | 3 | 2 | 0.000000 |  | 887286 |  |  | 0 | Must Start On | 09-10-2025 | As Soon As Possible | 0